AceDialer Mobile

iOS & Android — Subagents, Master Plan, Risks & Approval Gates

Prepared for ApTask leadership sign-off. Date: 2026-06-18. Status: Planning only — no application code written.

# 1. Executive Summary

Two specialized subagents have been created to take ApTask's existing AceDialer desktop softphone to the Apple App Store and Google Play Store as production-grade native apps (not WebView wrappers). A live, read-only audit of the existing codebase grounded this plan; nothing in the existing app was changed.

Both platforms are currently assessed at ~70% confidence — below the mandatory 95% gate — so no mobile code will be written until backend prerequisites are built and ApTask approves.

# 2. The Two Subagents

| Agent | ace-ios-mobile-agent | ace-android-mobile-agent |
| --- | --- | --- |
| Mission | Build, test, secure & prepare iOS for App Store review | Build, test, secure & prepare Android for Play review |
| Calling stack | Telnyx iOS SDK + CallKit + PushKit (VoIP push) | Telnyx Android SDK + FCM + full-screen intent + foreground service |
| Store gates | Privacy labels, Account Deletion (5.1.1v), TestFlight | Data Safety, restricted-perm avoidance, AAB + Play App Signing |
| Confidence | ~70% — gate NOT cleared | ~70% — gate NOT cleared |

Both are saved as runnable definitions in the repo at .claude/agents/. Each owns architecture, security, testing, store compliance, and release prep for its platform and coordinates on shared backend, UX, auth, and compliance.

# 3. Key Audit Findings (backend is not yet mobile-ready)

- No refresh tokens: a static, 15-minute JWT with no refresh-token endpoint — unworkable for a backgrounded phone app.

- No push infrastructure: the realtime service is a ping/pong stub and the device table is unused. Incoming calls cannot wake a backgrounded app today.

- SIP secret on the client: the per-user SIP password is returned to the client and stored in browser sessionStorage; on mobile it must move to Keychain/Keystore, ideally replaced by a short-lived token.

- Missing features: dispositions, call notes, contact search, JobDiva writeback, and self-service account deletion (a store requirement).

- Security gaps: MMS and greeting media are public URLs; live secrets (Telnyx, JWT, SIP, JobDiva, SendGrid, Microsoft) are committed in the repo .env and must be rotated.

# 4. Phased Master Plan

| Phase | Focus | Gate |
| --- | --- | --- |
| 0 | Discovery (live audit) | Complete |
| 1 | Architecture decisions + backend readiness | Sign-off B |
| 2 | MVP build (login, dialer, calls, history, SMS/MMS, voicemail, dispositions, settings) | After C (95%) |
| 3 | Platform integration (CallKit/PushKit; FCM/foreground service) | — |
| 4 | QA (functional, network, device, security, compliance) | — |
| 5 | Store prep (listings, privacy labels, Data Safety, reviewer login) | Sign-off E |
| 6 | Beta (TestFlight; Play internal/closed) | — |
| 7 | Production release | Sign-off F + G |
| 8 | Post-launch monitoring + Phase-2 features | — |

# 5. Top Risks (full register in 04-risk-register.md)

| # | Risk | Sev | Prob | Owner |
| --- | --- | --- | --- | --- |
| 11 | Account deletion missing (store requirement) | H | H | BE/Apps |
| 12 | Backend not mobile-ready | H | H | Backend |
| 3 | Push fails / inbound calls don't wake app | H | M | BE/Apps |
| 8 | Secrets exposed (committed repo secrets) | H | M | BE/Apps |
| 2 | Play rejection — restricted permissions | H | M | Android |
| 1 | Apple rejection — VoIP/CallKit misuse | H | M | iOS |
| 22 | Coding before 95% confidence | H | M | Apps |

# 6. What We Need From Leadership (decisions to unblock)

- Confirm ApTask will own the Apple Developer, Google Play, Firebase, and Telnyx accounts and all signing keys.

- Approve the mobile framework (native Swift/Kotlin recommended) — must match across both platforms.

- Approve building backend prerequisites: refresh tokens, device/push registration, push fan-out, short-lived SIP credentials, dispositions/notes, contact search, account deletion, signed media URLs.

- Decide V1 scope: outbound-first vs. inbound-at-launch.

- Provide/host Privacy Policy, Terms, Support, and data-deletion URLs (legal input on deletion + recording/SMS consent).

- Authorize rotation of the secrets currently committed to the repo.

# 7. Governance & Approval Gates

A Discovery → B Architecture → C 95% confidence gate (before ANY code) → D Pre-beta build → E Pre-submission checklist → F Submit approval → G Release approval. We are between A and B. No code, no commits, no submissions occur without explicit ApTask approval at the relevant gate.

Companion documents (in repo /docs/mobile/): 00 discovery report, 01 iOS deliverables, 02 Android deliverables, 03 master plan, 04 risk register, 05 final pre-submission checklist.